## Trial resource tool
Title:
TIMELINE OVERVIEW | Guidance
Award duration: XX months | Funder: XX
| Start Date |  | Pre-Award | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3
| End Date |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Trial Gantt chart
Protocol development
database build
Approvals
Set up | Number of sites/duration XX sites (Primary/social/secondary care?)
Recruitment | Target XX
intervention/setting | X arms
Follow up | timepoints/outcomes
interim analysis | month planned
Pilot | X
Close down data lock
Analysis/Write up
Drug procurement | add details
|  |  |  | Time (days) | [11 empty] | Time (days) | [11 empty] | Time (days)
|  |  |  | XX |  |  | XX |  |  | XX |  |  | XX |  |  | XX |  |  | XX |  |  | XX |  |  | XX |  |  | XX |  |  | XX |  |  | XX |  |  | XX
ACTIVITY | Description | Main CTU staff involved/leading activity | Pre-Award | Year 1 1: Year 1; Year 2 13: Year 2; Year 3 25: Year 3
Input to trial design and grant application preparation/submission including statistical validation |  | Stats, Methodologists, TMs
Randomisation/database |  | Stats, DMs, TMs
Terms of business |  | TMs
collaborations agreements |  | TMs
Site agreements/ financial appendix & SD agreement |  | STM, TMs
Technical Agreements |  | TMs
Contracts - IMP supplier |  | TMs
Other Vendor contracts SLAs/assessments |  | TMs
MTA's |  | TMs
Questionaire agreements |  | TMs
Online ePRO Provider Contract |  | TMs
Total |  |  |  | Year 1 1: 0; Year 1 4: 0; Year 1 7: 0; Year 1 10: 0; Year 2 13: 0; Year 2 16: 0; Year 2 19: 0; Year 2 22: 0; Year 3 25: 0; Year 3 28: 0; Year 3 31: 0; Year 3 34: 0
Protocol Development/Approvals
Initial feasibility |  | TMs, CTAs
PI meetings |  | All
Statistical simulations for protocol |  | Stats
Protocol Completed |  | All (led by STMs, TMs)
finalise costs for REC submission |  | STMs, TMs
Associated Documents for submission | consent/PIS/letters/outcomes/IRAS/translation /capacity/ | TMs
Sponsorship approval | monitor plan/delegation of duties/ | TMs
REC/HRA submission/approvals | covering letter/ finalise docs/book/attend/respond to comments/amend docs/portfolio | TMs
MHRA submission/approvals/additional docs | IRAS/covering letter/impd/label/diaries/IMP managment guide/IB/pharmacy/manufacturer | TMs
Risk Assessment | develop/meeting/review/sign off | All
Insurance |  | TMs
Portfolio Adoption | PAF | CTA
PPI | review of consent/PIS etc | STMs, TMs
IP |  | STMs, TMs
Any trial specific training for CTU staff | consider each staff group i.e. stats, trial managers | All
TOTAL |  |  |  | Year 1 1: 0; Year 1 4: 0; Year 1 7: 0; Year 1 10: 0; Year 2 13: 0; Year 2 16: 0; Year 2 19: 0; Year 2 22: 0; Year 3 25: 0; Year 3 28: 0; Year 3 31: 0; Year 3 34: 0
Database development
Agree randomisation requirements |  | Stats, DMs
DB Agree Specification &CRF development |  | DMs, TMs, Stats, STMs
Database build |  | DMs, TMs, Stats, STMs
DB User Acceptance Testing |  | All
DMP and DVP |  | DMs, Stats, STM, TMs
Randomisation testing |  | Stats, DMs
TOTAL |  |  |  | Year 1 1: 0; Year 1 4: 0; Year 1 7: 0; Year 1 10: 0; Year 2 13: 0; Year 2 16: 0; Year 2 19: 0; Year 2 22: 0; Year 3 25: 0; Year 3 28: 0; Year 3 31: 0; Year 3 34: 0
Study set up/ Project management |  |  |  | Year 1 1: Year 1
Trial Timelines | Gantt, Project Management plan, reporting schedule | STMs
Funder requirments pre trial | protocol approval, Budget changes, funder milestones, TOC member approvals | STMs
Site Feasibility | XX sites - create form, send to sites, chase, collate feedback, TMG | TMs, CTA
Study Launch | Launch/Investigator meeting | All
Vendor Management | Vendor assessments/contracts/schedules | TMs
Financial Management set up | budget/invoices/finance log update continually set up | STMs
Trial registration | ISCTRN/clinicaltrials.gov | CTA, TMs
Eudract |  | TMs
ePRO Provision Set-up |  | DMs, Stats, TMs
eConsent |  | DMs, TMs
Biobanking |  | TMs, CTA
Central support facilities |  | STMs, TMs
IT infrastructure/data transfer |  | STMs, DMs, TMs,
Sample transfers |  | CTA
purchase consumables |  | CTA
IMP supply chain |  | TMs, STM
Protocol Publication |  | All
TOTAL Days
Site Set up | XX sites over XX Months | TMs, CTA
ISF | Setup, printing, distribution | CTA
TMF set up |  | CTA
SIV | preparation and attendance | All
Confirmation of C&C/greenlight/approvals |  | TMs, CTA, DM
Site Documentation | Delegaton log, Training log, eligibility/consent proforma, Accountability, blinding, screening,version control | TM, CTA
Monitoring set up | Central Monitoring logs, template documents, pharmacy, labs | TM
Pharmacy set up | Pharmacy Manual, SmPC, IB, IMPD, Prescriptions, Accountability, Label, IMP manufacture, Placebo manufacture - see under randomisation system set up for DM time | TM
Other department set up - e.g. radiology |  | TM
Laboratories - e.g. NHS/university | Lab Manual & associated documents, equipment - for data side see below | TM
TOTAL |  |  |  | Year 1 1: 0; Year 1 4: 0; Year 1 7: 0; Year 1 10: 0
Recruitment Period |  |  |  | Year 1 1: Year 1
Weekly contact/advice with sites | Depends on number of sites | TMs, CTA, DMs
regular newletter updates |  | TMs, CTA
Data Management | data cleaning, management of data queries | DM
Webinars/training/updates |  | All
Site Management | query resolution - depends on number of sites, and complexity of trial, scale of data, experience of sites | TMs, CTA
Trial Amendments | preparation, submission, communication to sites | STM, TMs, CTA
Manage deviations/violations/serious breaches | documentation and CAPAs | All (led by TM)
Central Monitoring | Central, preparation, reporting, resolution, monitoring plan updates | TMs, DMs, CTA
Onsite / remote monitoring | preparation, reporting, resolution, monitoring plan updates | TMs
Manage/review recruitment retention | upload of accruals | CTAs
Financial management | consumables, site payments,salaries, vendors, collaborators | STMs, TMs, CTAs
Safety reporting- continuous | SAE management, SAE reconciliation | TMs, CTA, STM
DSUR annually |  | TMs, CTA, STM
REC safety report |  | STM, TMs, CTA
MHRA reporting (including non-CE marked devices) |  | STM, TMs, CTA
Funder Reporting | drafting/review/submit ? Quarterly / annual depending on funder | STM, TMs, DMs, CTA
REC APR | prepare and submit | STMs, TMs
SUSARs, USMs | reporting | STM, TMs, CTA
Risk Assessment | annual review and update | All
Consumables/equipment servicing/callibration |  | CTAs
IMP management |  | DMs
shipping of samples |  | CTAs
Intervention specific requirements |  | STMs, TMs, DMs
Follow up data requirements |  | DMs
TMF maintenance |  | CTAs
Development of Statistical Analysis Plan |  | All (led by Stats)
TOTAL - days
Trial oversight meetings and interim analyses |  |  |  | Year 1 1: Year 1
Internal trial management | Regular meetings | All
Monthly TMG | data download/reports | DMs
| Attendance | All
| Terms of Reference | TMs
| Agenda/planning/minutes | TMs, CTAs
DMC 2x year | data download/reports | DMs, Stats
| Terms of Reference/Charter/Template reports/Funder approval | TMs
| Attendance | All
| Agenda/planning/minutes | TMs, CTAs
TSC (or TOC) 2x year | data download/reports | DMs, Stats
| Terms of Reference/Charter/Template reports/Funder approval | TMs, CTAs
| Attendance | All
| Agenda/planning/minutes | TMs, CTAs
Clinical Events Committee | Preparation/agenda/report, depends on complexity of data to be adjudicated if applicable | TMs, DMs, Stats
Interim analysis |  | Stats
Implementation of interim analysis findings | Change in randomisation/database/protocol amendments | All
TOTAL |  |  |  | Year 1 1: 0; Year 1 4: 0; Year 1 7: 0; Year 1 10: 0
Close down |  |  |  | Year 1 1: Year 1
End of Study notifications | REC, MHRA etc | STMs, TMs
Trial Registration | ISRCTN/clinicaltrials.gov | TMs
Eudract |  | TMs, stats
SAE reconciliation |  | TMs
Data Management | final data cleaning and queries, data lock, screening data - depends on complexity of data and number of centres | DMs
Data Lock |  | DMs
Conduct final statistical analysis according to SAP | Validation & writing End of Trial Statistical Report | Stats
Management of recruitment closure | closedown visits and completion of final monitoring actions | TMs, CTAs
Safety management | Final reconciliation | TMs
Funder Reporting |  | All (led by STM)
Site Closure | ISF review, Monitoring, Pharmacy, Laboratories, calls, reports, notifications, site archiving | TMs, CTAs
Study equipment management |  | CTAs
End of study reporting | REC, MHRA, EudraCT, patient/participant facing | All (led by STM)
Dissemination | Results publication, PPI&E, dissemination of results, conferences | All (led by STM)
Anonymisation of dataset/data sharing |  | DMs
Archiving (including of data) | TMF, data to sites | DMs, CTAs
Financial reconciliation |  | STMs
TOTAL
TOTAL RESOURCE REQUIREMENT (days/hours) | bar: Year 1 1; Year 1 4; Year 1 7; Year 1 10; Year 2 13; Year 2 16; Year 2 19; Year 2 22; Year 3 25; Year 3 28; Year 3 31; Year 3 34
TOTAL FTE | 220 x days in a typical working year